## Sheet1
Risk | Sprint | Sprint Goal | Start Date | End Date | Duration | Responsible | Status
Medium | 1 | Project setup and initial architecture | Jan 5 2025 | Jan 18 2025 | 2 weeks | Uriarte | Completed
Medium | 2 | Core user functionality | Jan 19 2025 | Feb 1 2025 | 2 weeks | Uriarte | Completed
High | 3 | Order processing and kitchen display | Feb 2 2025 | Feb 15 2025 | 2 weeks | Uriarte | Completed
High | 4 | Financial systems | Feb 16 2025 | Mar 1 2025 | 2 weeks | Uriarte | Completed
Medium | 5 | Inventory and add-on management | Mar 2 2025 | Mar 15 2025 | 2 weeks | Uriarte | Completed
High | 6 | Self-checkout and customer experience | Mar 16 2025 | Mar 29 2025 | 2 weeks | Uriarte | Completed
Medium | 7 | Reporting and analytics | Mar 30 2025 | Apr 12 2025 | 2 weeks | Uriarte | Completed
Medium | 8 | System optimization and monitoring | Apr 13 2025 | Apr 26 2025 | 2 weeks | Uriarte | Completed
Low | 9 | Core features and development progress | Apr 27 2025 | May 10 2025 | 2 weeks | Uriarte | Completed
Low | 10 | Completing core functionality | May 11 2025 | May 24 2025 | 2 weeks | Uriarte | Completed
High | 11 | Advanced POS System Enhancement | May 25 2025 | Jun 7 2025 | 2 weeks | Uriarte | Completed
High | 12 | Staff Management System Overhaul | Jun 8 2025 | Jun 21 2025 | 2 weeks | Uriarte | Completed
High | 13 | AI Chatbot Integration and Customer Experience | Jun 22 2025 | Jul 5 2025 | 2 weeks | Uriarte | Completed
Medium | 14 | Advanced Menu Management and Theme System | Jul 6 2025 | Jul 19 2025 | 2 weeks | Uriarte | Completed
Medium | 15 | Advanced Analytics and Dashboard Enhancement | Jul 20 2025 | Aug 2 2025 | 2 weeks | Uriarte | Completed
Medium | 16 | Mobile Optimization and System Finalization | Aug 3 2025 | Aug 16 2025 | 2 weeks | Uriarte | Completed
Critical | 17 | Production Deployment and System Maintenance | Aug 17 2025 | Sep 7 2025 | 3 weeks | Uriarte | Completed
High | 18 | Menu Availability System & Database-Driven Category | Sep 8 2025 | Sep 21 2025 | 2 weeks | Uriarte | Completed
Medium | 19 | Menu Availability Feature Implementation | Sep 8 2025 | Sep 11 2025 | 4 days | Uriarte | Completed
Critical | 20 | Critical Bug Fixes | Sep 11 2025 | Sep 11 2025 | 1 day | Uriarte | Completed
High | 21 | Database-Driven Category System Migration | Sep 12 2025 | Sep 13 2025 | 2 days | Uriarte | Completed
High | 22 | Architecture Transformation | Sep 15 2025 | Sep 15 2025 | 1 day | Uriarte | Completed
Medium | 23 | Performance Optimization | Sep 16 2025 | Sep 17 2025 | 2 days | Uriarte | Completed
Medium | 24 | Inventory Integration | Oct 2 2025 | Oct 2 2025 | 1 day | Uriarte | Completed
Low | 25 | Inventory System Cleanup | Oct 3 2025 | Oct 3 2025 | 1 day | Uriarte | Completed
Low | 26 | Receipt Number Fix | Oct 3 2025 | Oct 3 2025 | 1 day | Uriarte | Completed
High | 27 | Database Connection Pool Optimization | Oct 4 2025 | Oct 4 2025 | 1 day | Uriarte | Completed
High | 28 | Payment Verification System | Oct 10 2025 | Oct 14 2025 | 5 days | Uriarte | Completed
Medium | 29 | Socket.io Authentication Fix | Oct 15 2025 | Oct 15 2025 | 1 day | Uriarte | Completed
Medium | 30 | Real-Time Inventory System | Oct 15 2025 | Oct 15 2025 | 1 day | Uriarte | Completed
Medium | 31 | Dynamic Size Management System | Oct 16 2025 | Oct 16 2025 | 1 day | Uriarte | Completed
Critical | 32 | PayMongo GCash Integration | Nov 5 2025 | Nov 9 2025 | 5 days | Uriarte | Completed
High | 33 | Supabase Storage Migration | Nov 19 2025 | Nov 23 2025 | 5 days | Uriarte | Completed
Low | 34 | Frontend URL Handling Fixes | Nov 19 2025 | Nov 21 2025 | 3 days | Uriarte | Completed
High | 35 | Payroll Enhancement System | Nov 20 2025 | Nov 25 2025 | 6 days | Uriarte | Completed
Medium | 36 | Government Deductions Implementation | Nov 24 2025 | Nov 24 2025 | 1 day | Uriarte | Completed
Medium | 37 | Role-Based Expense Workflow System | Nov 25 2025 | Nov 25 2025 | 1 day | Uriarte | Completed
High | 38 | Staff Scheduling System with Drag-Drop Calendar | Dec 1 2025 | Dec 4 2025 | 4 days | Uriarte | Completed